## Sheet1
task | stage | start | end | completion
Literature Review | Project Proposal | 2021-07-01 | 2021-09-30 | 1
Defining aims and objectives | Project Proposal | 2021-07-01 | 2021-07-08 | 1
EDA | Project Proposal | 2021-06-01 | 2021-06-11 | 1
App development | Project Proposal | 2021-06-11 | 2021-08-31 | 0.8
Simulation #1: run app | Project Proposal | 2021-09-01 | 2021-09-08 | 1
Deliverable: Project Proposal (write-up & submission) | Project Proposal | 2021-10-01 | 2021-10-31 | 1
Explore & fix results from simulation #1 | Progress Report 1 | 2021-09-08 | 2021-11-08 | 0.5
Refine requirements (i.e. methodology) | Progress Report 1 | 2021-11-01 | 2021-11-23 | 0.2
Deliverable: Progress Report 1 | Progress Report 1 | 2021-11-23 | 2021-12-15 | 0.1
Simulation #2: run app based on new requirements | Progress Report 2 | 2021-12-27 | 2022-01-15 | 0
Explore & fix results from simulation #2 | Progress Report 2 | 2022-01-16 | 2022-01-31 | 0
Deliverable: Progress Report 2 (write-up & submission) | Progress Report 2 | 2022-02-01 | 2022-02-28 | 0
Refine methodology based on new developments | Research paper | 2022-03-01 | 2022-02-14 | 0
Deployment of prototype app & final simulation | Research paper | 2022-03-15 | 2022-03-19 | 0
Deliverable: Research Paper (write up, prof-read & submission) | Research paper | 2022-03-20 | 2022-04-30 | 0